## Sheet1
Task ID | Task Name | Description content | Task assignee | Priority | Status | Start date | Due date | List | Tags | Subtasks | Sprint Phase | Dependencies | Acceptance Criteria | Technical Notes
T-001 | Freeze frontend-consumed API response contracts | Document and freeze the exact response shapes for student enrollments, progress, streaks, and active bug-fix endpoints so frontend work can proceed without guessing. This removes silent rendering bugs caused by inconsistent payloads. | Zeyad | 2 | To Do | 46135.0001 | 46135.0001 | Backend Bug Fixes | backend,contract,day-1,api | Audit current response shapes¦Standardize final route shape¦Publish success empty and error payloads¦Share contract note with Jimmy and Mohamed¦Provide stub payloads for unfinished routes | Day 1: Setup + Contracts + Mocks | None — can be done in parallel | [ ] Each targeted endpoint has a documented final response shape¦[ ] Each route includes at least one sample payload¦[ ] Empty-state and error-state payloads are defined¦[ ] Jimmy can implement pages without waiting for live backend changes | APIs: /api/enrollments/student, /api/progress/overall, /api/progress/courses, /api/streaks/me. Modules: server/src/api/enrollment.routes.ts, server/src/api/progress.routes.ts. If final implementation is not ready, provide stub JSON with the final contract.
T-002 | Freeze gamification API and shared type contracts | Lock the gamification payload shapes for profile, badges, leaderboard, activity, admin settings, rules, and reports so frontend and testing work can proceed independently. | Mohamed | 2 | To Do | 46135.0001 | 46135.0001 | Gamification System | gamification,contract,day-1,shared-types | Review current gamification routes and shared types¦Finalize response shapes in shared types¦Publish student and admin sample payloads¦Define query keys and cache invalidation notes¦Share contract pack with Jimmy and QA | Day 1: Setup + Contracts + Mocks | None — can be done in parallel | [ ] Shared gamification types reflect the intended API shape¦[ ] Student and admin gamification sample payloads exist¦[ ] Query keys and refresh behavior are documented¦[ ] Jimmy can render gamification UI from samples without backend dependency | APIs: /api/gamification/me, /api/gamification/me/badges, /api/gamification/leaderboard, /api/gamification/activity, /api/admin/gamification/*. Files: shared/gamification.types.ts and gamification routes/services.
T-003 | Define security error and middleware contract | Create a stable contract for auth failures, rate-limit responses, and high-risk middleware behavior so backend and frontend teams know exactly how protected routes will behave this week. | Shady | 2 | To Do | 46135.0001 | 46135.0001 | Security Hardening | security,contract,day-1,middleware | Audit auth session and rate-limit middleware behavior¦Define standard error response shape¦List top-risk routes following this contract¦Publish local developer testing notes¦Share with Zeyad Jimmy and Youssef | Day 1: Setup + Contracts + Mocks | None — can be done in parallel | [ ] Security error response shape is documented¦[ ] Protected route categories are listed¦[ ] Local developer testing guidance is available¦[ ] No team member is blocked by unclear auth behavior | Modules: server/src/index.ts, server/src/middleware/*. Avoid changing feature contracts while defining security behavior.
T-004 | Prepare frontend fixture adapters for unstable APIs | Set up local mock and fixture support so frontend bug-fix and gamification UI work can proceed even if backend routes are incomplete or unstable. | Jimmy | 2 | To Do | 46135.0001 | 46135.0001 | Frontend Bug Fixes | frontend,mock-required,day-1,fixtures | Create fixture payloads for enrollments progress streaks gamification and AI¦Add helper to switch between live and fixture data¦Validate fixture rendering on student pages¦Document how to toggle fixture mode¦Flag contract mismatches immediately | Day 1: Setup + Contracts + Mocks | Depends on T-001 and T-002 contracts when available; otherwise use current best-known shapes and update later | [ ] Student courses page renders from fixture data¦[ ] Student dashboard renders from fixture data¦[ ] Student gamification page renders from fixture data¦[ ] Fixture mode can be enabled without editing multiple files | Files: client/src/pages/* and lightweight mock helpers under client/src. Do not edit gamification-owned components without Mohamed’s contract signoff.
T-005 | Define AI orchestration contract and stub executor | Freeze the request and response schema for the AI workflow orchestrator and provide a deterministic stub implementation so UI and integration work can continue before live AI logic is complete. | Youssef | 2 | To Do | 46135.0001 | 46135.0001 | AI Features | ai,contract,day-1,mock-required | Define orchestration request payload¦Define orchestration response with fallback and trace¦Create sample request and response JSON¦Define deterministic stub outputs¦Share contract with Jimmy and Mohamed | Day 1: Setup + Contracts + Mocks | None — can be done in parallel | [ ] AI orchestration request schema is documented¦[ ] AI orchestration response schema is documented¦[ ] Stub responses exist for success and fallback scenarios¦[ ] Frontend can build against the stub without waiting for AI backend completion | Target API: POST /api/ai-orchestra/execute. Constraint: one stable schema only and no midweek contract drift.
T-006 | Fix student courses page data parsing and rendering stability | Fix the student courses page so it correctly renders paginated enrollment responses and never silently displays an empty list for valid data. | Jimmy | 2 | To Do | 46136.0418 | 46137.0001 | Frontend Bug Fixes | frontend,student,day-2-3,bugfix | Audit current parsing logic¦Support paginated data response shape¦Add explicit error and empty-state UI¦Validate with fixture and live responses¦Record before and after screenshots | Day 2–3: Core Implementation | None — can be done in parallel with live backend fixes using fixtures | [ ] Courses render correctly when API returns paginated data¦[ ] Real empty enrollment state shows intentional messaging¦[ ] API error shows intentional error state¦[ ] No silent blank list remains on the page | Files: client/src/pages/student-courses.tsx and any shared student hooks if needed. If live route remains unstable, keep fixture adapter until Zeyad confirms contract.
T-007 | Fix student dashboard data aggregation and fallback states | Stabilize student dashboard rendering across enrollments, progress, and streak responses so the page remains usable even when one source is empty or temporarily unavailable. | Jimmy | 2 | To Do | 46136.0418 | 46137.0001 | Frontend Bug Fixes | frontend,student,day-2-3,dashboard | Audit current dashboard fetch and parsing logic¦Normalize response handling¦Add empty loading and partial-data states¦Validate widgets with live and fixture payloads¦Document remaining backend mismatches | Day 2–3: Core Implementation | None — can be done in parallel with fixtures | [ ] Dashboard loads with full data when all endpoints succeed¦[ ] Dashboard still renders partial UI when one endpoint fails¦[ ] Empty state messaging is clear and intentional¦[ ] No silent render failures remain | Files: client/src/pages/student-dashboard.tsx, client/src/hooks/useStudentDashboard.ts. APIs: enrollments progress streak routes.
T-008 | Normalize student and teacher API route shapes | Fix backend route inconsistencies causing frontend bugs, especially array versus object drift, missing wrappers, and incompatible empty-state behavior. | Zeyad | 2 | To Do | 46136.0418 | 46137.0001 | Backend Bug Fixes | backend,api,day-2-3,bugfix | Identify top impacted routes¦Normalize response wrappers and pagination metadata¦Ensure status codes and error payloads are consistent¦Verify affected consumers¦Publish route changelog | Day 2–3: Core Implementation | None — can be done in parallel | [ ] Targeted routes return consistent documented shapes¦[ ] Empty responses are explicit and predictable¦[ ] Error responses use standard structure¦[ ] Frontend consumers can parse routes without custom hacks per page | Files: selected server/src/api/*.ts excluding gamification and security-owned routes. Do not change gamification or security routes without coordination.
T-009 | Complete persistent lesson completion event flow | Ensure lesson completion is durably recorded in the database and survives refresh even when points are disabled. This is the critical path for making gamification reliable. | Mohamed | 2 | To Do | 46136.0418 | 46137.0001 | Gamification System | gamification,backend,day-2-3,critical-path | Audit lesson completion endpoint to event persistence¦Ensure completion event is written even when points are zero¦Verify activity endpoint restores completed lessons¦Validate course completion behavior on last lesson¦Document event persistence rules | Day 2–3: Core Implementation | None — can be done in parallel | [ ] Completing a lesson creates a durable completion record¦[ ] Refreshing the lesson viewer shows completed lessons correctly¦[ ] Duplicate completion remains idempotent¦[ ] Course completion fires only under valid final-lesson conditions | Files: lesson completion route, gamification service, activity route, lesson viewer consumer. Completion persistence must not depend solely on points being enabled.
T-010 | Complete student gamification profile refresh behavior | Make the student gamification experience update immediately after completions and load correctly from persisted state on revisit. | Mohamed | 2 | To Do | 46136.0418 | 46137.0001 | Gamification System | gamification,frontend,day-2-3,student | Review query invalidation and refresh behavior¦Ensure profile badges and activity feed update¦Validate empty disabled and active states¦Verify route mounting and auth behavior¦Produce UI verification checklist | Day 2–3: Core Implementation | Depends on T-009 preferred but can be mocked in parallel | [ ] Student gamification page updates after completion actions¦[ ] Refreshing the page shows persisted state¦[ ] Empty and disabled states are accurate¦[ ] No endpoint returns 404 for mounted gamification routes | Files: gamification pages hooks components and route mounting. Use shared gamification types as source of truth.
T-011 | Implement admin gamification settings and rules stability pass | Stabilize the admin-side gamification controls so the platform can safely configure points, naming, badges, and feature flags during integration. | Mohamed | 3 | To Do | 46136.0418 | 46137.0001 | Gamification System | gamification,admin,day-2-3 | Validate settings get and put flow¦Validate default rule seeding behavior¦Verify rules update validation and persistence¦Validate admin badges list create and update contract¦Document admin-side usage and constraints | Day 2–3: Core Implementation | None — can be done in parallel | [ ] Admin can fetch and update gamification settings¦[ ] Default rules exist or are safely seeded¦[ ] Invalid rule updates are rejected predictably¦[ ] Badge CRUD contract is usable by frontend consumers | Files: server/src/api/admin-gamification.routes.ts, gamification service, admin hooks if needed. No frontend polish beyond what is needed to validate contract.
T-012 | Harden rate limiting and sensitive middleware behavior | Improve baseline protection on sensitive routes, especially auth, AI, uploads, and high-risk POST endpoints, without disrupting normal developer flow. | Shady | 2 | To Do | 46136.0418 | 46137.0001 | Security Hardening | security,backend,day-2-3,rate-limit | Audit current rate-limit configuration and key generation¦Apply safe coverage to sensitive endpoints¦Standardize middleware behavior and error payloads¦Validate local ergonomics and proxy IP handling¦Document route coverage and thresholds | Day 2–3: Core Implementation | None — can be done in parallel | [ ] Sensitive routes are protected by appropriate rate limiting¦[ ] IPv4 and IPv6 and proxy-safe key behavior is correct¦[ ] Error responses follow the documented security contract¦[ ] Local development still works with documented expectations | Files: server/src/index.ts and middleware files. Avoid breaking legitimate QA and dev workflows.
T-013 | Harden upload anti-cheat and restricted endpoint protections | Ensure upload and proctoring-related endpoints enforce role checks, input validation, and safe error behavior because these are high-risk surfaces. | Shady | 2 | To Do | 46136.0418 | 46137.0001 | Security Hardening | security,uploads,anti-cheat,day-2-3 | Audit recording upload and anti-cheat routes¦Validate role-based access on view and write actions¦Verify file size and type restrictions¦Validate suspicious activity logging¦Publish risk findings and remediations | Day 2–3: Core Implementation | None — can be done in parallel | [ ] Unauthorized users cannot access protected upload and proctoring endpoints¦[ ] Upload validation rejects invalid files safely¦[ ] High-risk route failures are logged consistently¦[ ] Risk register captures remaining issues clearly | Files: server/src/api/anti-cheat.routes.ts, server/src/api/recording-upload.routes.ts, related middleware and services.
T-014 | Build AI orchestration service shell | Implement the orchestration service entrypoint that can receive a structured task, route it through the intended workflow, and return a traceable response shape. | Youssef | 2 | To Do | 46136.0418 | 46137.0001 | AI Features | ai,backend,day-2-3,orchestrator | Create orchestration service module and route scaffold¦Parse and validate request payload¦Implement stub-to-live routing structure¦Return deterministic response with trace metadata¦Document execution flow | Day 2–3: Core Implementation | None — can be done in parallel | [ ] Orchestration endpoint exists and accepts the frozen request schema¦[ ] Endpoint returns valid structured responses¦[ ] Trace metadata is included¦[ ] Service can run in stub mode without external AI dependencies | Files: AI routes and services. Constraint: one working orchestrated path this week is enough and overbuilding should be avoided.
T-015 | Implement one real AI orchestration workflow with fallback | Deliver one functioning workflow through the orchestrator using existing lesson retrieval or chat capability where possible and a graceful fallback when AI infra is unavailable. | Youssef | 2 | To Do | 46136.0418 | 46137.0001 | AI Features | ai,orchestrator,day-2-3,fallback | Select one workflow path¦Integrate existing lesson retrieval or AI chat service¦Add fallback path for missing key or unavailable vector DB¦Verify response consistency across success and fallback¦Document operational dependencies | Day 2–3: Core Implementation | Depends on T-014 | [ ] One orchestrated workflow works end to end¦[ ] Missing AI provider or retrieval infra returns graceful fallback¦[ ] Response schema stays identical in success and fallback modes¦[ ] Operational dependencies are documented | Files: server/src/api/ai-chat.routes.ts, server/src/services/ai.service.ts, server/src/services/lesson-digestion.service.ts, orchestration service.
T-016 | Replace frontend mocks with live backend routes where ready | Swap fixture-backed flows to live APIs for completed modules and verify the UI behaves the same with real data. | Jimmy | 2 | To Do | 46138.0001 | 46138.0001 | Integration & Testing | frontend,integration,day-4 | Identify routes ready for live integration¦Toggle pages and hooks from fixtures to live mode¦Validate all state modes with live data¦Record integration issues and hand back to owners¦Keep unresolved flows on fixture mode with explicit flag | Day 4: Integration | Depends on T-008, T-010, and T-015 where relevant; if not ready keep mocks and document carry-over | [ ] Live-integrated pages behave the same as fixture-backed versions¦[ ] Broken live flows are documented with owner and route¦[ ] No unresolved integration issue silently blocks the UI¦[ ] Remaining mock-backed flows are clearly marked for carry-over | Do not wait on unfinished routes. Keep fixture fallback where needed.
T-017 | Run backend contract verification sweep | Verify all changed backend routes against their documented contracts and catch mismatches before final testing day. | Zeyad | 2 | To Do | 46138.0001 | 46138.0001 | Integration & Testing | backend,integration,day-4,verification | Re-run target route requests using sample payload scenarios¦Compare live responses to documented schema¦Fix drift or document exceptions¦Coordinate with Mohamed for gamification route checks¦Publish backend verification summary | Day 4: Integration | Depends on core backend and gamification route work being complete enough for validation | [ ] All changed routes are checked against documented schemas¦[ ] Contract mismatches are fixed or explicitly documented¦[ ] Status codes are verified¦[ ] Backend verification summary is published | Use curl or Postman or equivalent smoke tooling. No new scope should be added during verification.
T-018 | Run security regression sweep on changed endpoints | Validate that this week’s changed or added routes still meet baseline security expectations after integration. | Shady | 2 | To Do | 46138.0001 | 46138.0001 | Integration & Testing | security,integration,day-4,regression | Re-test protected endpoints with invalid auth and role¦Re-test rate-limited endpoints¦Re-test upload and AI-related sensitive routes¦Log any high-severity findings¦Publish regression summary and residual risks | Day 4: Integration | Depends on core implementation tasks being complete enough for validation | [ ] Protected endpoints reject unauthorized requests correctly¦[ ] Sensitive endpoints respect new middleware behavior¦[ ] Any residual security issues are severity-tagged¦[ ] Regression summary is published | Coordinate with Youssef on AI endpoint behavior and Zeyad on generic routes.
T-019 | Run gamification integration checkpoint | Verify the full gamification slice together across backend, frontend, and admin configuration so final testing is based on a working end-to-end path. | Mohamed | 2 | To Do | 46138.0001 | 46138.0001 | Integration & Testing | gamification,integration,day-4,checkpoint | Validate lesson completion to event persistence¦Validate student profile and activity refresh¦Validate admin settings rules and badges flows¦Validate leaderboard and report state behavior¦Capture known issues and assign owners immediately | Day 4: Integration | Depends on T-009, T-010, T-011, and Jimmy’s related frontend integration | [ ] Student completion updates gamification consistently¦[ ] Refresh preserves gamification-related state¦[ ] Admin flows are testable end to end¦[ ] Known issues are logged with owner and severity | No unresolved issue leaves the checkpoint without owner or workaround.
T-020 | Run AI orchestration integration checkpoint | Validate the orchestrator in a realistic environment with auth, lesson context if available, and failure simulation. | Youssef | 2 | To Do | 46138.0001 | 46138.0001 | Integration & Testing | ai,integration,day-4,checkpoint | Test authenticated orchestration request¦Test lesson-context path if available¦Test fallback path with disabled AI dependency¦Validate trace metadata and output shape¦Publish integration summary | Day 4: Integration | Depends on T-014 and T-015; frontend consumer is optional | [ ] Orchestrator works with authenticated request¦[ ] Success path returns expected structured response¦[ ] Failure path returns graceful fallback¦[ ] Trace metadata is visible and useful | Backend-first validation is acceptable this week.
T-021 | Final frontend regression pass and evidence collection | Run a final regression sweep across all touched UI flows and produce evidence for what was fixed and what still needs follow-up. | Jimmy | 2 | To Do | 46139.0001 | 46139.0001 | Frontend Bug Fixes | frontend,day-5,regression,documentation | Re-test student pages touched this week¦Re-test teacher and admin pages touched this week¦Capture screenshots or short videos¦Update frontend bug-fix doc¦Log carry-over issues clearly | Day 5: Testing + Polish | Depends on Day 4 integration tasks | [ ] Every touched UI route has a tested outcome¦[ ] Evidence exists for fixed flows¦[ ] Remaining issues are documented clearly¦[ ] No silent blank-state bug remains in tested areas | Documentation target: docs/frontend-weekly-bugfixes.md. Use a junior-friendly checklist format.
T-022 | Final backend smoke run and route changelog | Perform final backend smoke validation and publish a concise changelog of fixed routes, payload changes, and known issues. | Zeyad | 2 | To Do | 46139.0001 | 46139.0001 | Backend Bug Fixes | backend,day-5,smoke-test,documentation | Run final route smoke tests¦Confirm key routes return documented shapes¦Compile changed-route summary¦Flag unresolved backend issues¦Share final handoff note | Day 5: Testing + Polish | Depends on Day 4 verification complete | [ ] Smoke-tested routes pass expected checks¦[ ] Changelog includes route change and risk¦[ ] Known unresolved issues are explicit¦[ ] Final note is ready for lead review | Focus on routes touched this sprint only. No broad cleanup outside committed scope.
T-023 | Final security signoff and risk register update | Provide final security review for this sprint’s changes and update the risk register with anything that remains open. | Shady | 2 | To Do | 46139.0001 | 46139.0001 | Security Hardening | security,day-5,signoff,risk-register | Review all security-related changes¦Confirm mitigations on high-risk endpoints¦Update residual risk entries¦Write final signoff summary¦Escalate any critical blocker immediately | Day 5: Testing + Polish | Depends on Day 4 security regression complete | [ ] Security status is documented for changed areas¦[ ] Residual risks are severity-tagged and owned¦[ ] No critical issue is left undocumented¦[ ] Final signoff summary is shared | Documentation targets: docs/security-hardening-weekly.md and docs/security-risk-register.md.
T-024 | Final AI runbook and demo-ready validation | Finalize documentation and validation for the AI orchestration slice so it can be demonstrated and handed off cleanly. | Youssef | 3 | To Do | 46139.0001 | 46139.0001 | AI Features | ai,day-5,runbook,demo | Validate final success and fallback responses¦Finalize environment requirements¦Finalize runbook and troubleshooting notes¦Capture one demo scenario¦Log next-step improvements for future sprint | Day 5: Testing + Polish | Depends on AI integration checkpoint complete | [ ] AI runbook is complete¦[ ] Demo scenario is validated¦[ ] Environment requirements are documented¦[ ] Known next steps are separated from current sprint completion | Documentation targets: docs/ai-orchestra-contract.md and docs/ai-orchestra-runbook.md.
T-025 | Final cross-team integration review and sprint closeout | Run the final cross-team review, ensure every module has evidence and documentation, and produce the sprint closeout summary. | Mohamed | 2 | To Do | 46139.0001 | 46139.0001 | Integration & Testing | integration,lead,day-5,closeout | Collect final validation summaries from all owners¦Review unresolved issues and decide keep fix or escalate¦Produce sprint closeout note¦Confirm demo-ready flows¦Confirm next sprint carry-over list | Day 5: Testing + Polish | Depends on all Day 5 validation tasks | [ ] Every module owner submits final status and evidence¦[ ] Carry-over issues have owner and reason¦[ ] Sprint closeout note is complete¦[ ] Demo-ready flows are identified clearly | Mohamed acts as integration lead. No issue closes without evidence or explicit carry-over note.